SANJIVANI UNIVERSITY, KOPARGAON

B.Tech — Artificial Intelligence & Data Science

UNIT-2 AGILE MINI-PROJECT

Agile Project Planning Report

Student Record and Academic Management Platform

Submitted by

Om

PRN: 2125UDSM1037

Program: B.Tech (Artificial Intelligence & Data Science)

Institution: Sanjivani University, Kopargaon, Maharashtra

# Table of Contents

1. Introduction & Business Problem Recap	3

2. Agile Product Vision	3

3. Scrum Team Structure & Roles and Responsibilities	4

4. Epic Documentation	5

5. User Story Repository & Acceptance Criteria	5

6. Prioritized Product Backlog	11

7. Story Point Estimation Sheet	12

8. Sprint Planning & Sprint Backlog	13

9. Scrum Board	15

10. Burndown Chart	16

11. Simulated Scrum Ceremonies	16

12. Agile Framework Comparison	17

13. Project Timeline & Release Roadmap	18

14. Conclusion	18

# 1. Introduction & Business Problem Recap

This report documents the Unit-2 Agile deliverables for the Student Record and Academic Management Platform, building on the Product Discovery work completed in Unit 1. The platform is intended to help educational institutions efficiently manage student records, attendance, academic performance, course registration, and reporting through a scalable, secure, web-based application.

The stakeholders identified during discovery — students, faculty, administrators, and system administrators — remain central to every Epic, User Story, and Sprint plan defined below. This document translates the Product Vision and Business/Functional/Non-functional Requirements into an actionable Agile plan: Scrum roles, Epics, User Stories, a prioritized Backlog, Story Point estimates, a Sprint Plan, a Scrum Board, simulated Scrum ceremonies, and a comparison of Agile frameworks with a recommendation for this project.

# 2. Agile Product Vision

“Develop a secure and user-friendly Student Record and Academic Management Platform that enables educational institutions to efficiently manage student records, attendance, academic performance, course registration, and reporting through a scalable web-based application.”

## Overall Product Objective

To digitize and centralize the academic record-keeping workflow of an institution — replacing fragmented, manual processes with a single, reliable, and secure platform.

## Primary Users

- Students — view profile, attendance, marks, and results.

- Faculty Members — record attendance, enter marks, and generate course-level reports.

- Administrators — manage students, courses, enrollments, and institution-wide reporting.

- System Administrators — manage roles, permissions, and platform security.

## Business Benefits

- Reduced administrative overhead through automation of record-keeping.

- Improved data accuracy and a single source of truth for academic records.

- Faster, self-service access to attendance and results for students.

- Timely, automated notifications that reduce missed exams and low-attendance surprises.

## Measurable Success Criteria

- 100% of student, course, attendance, and marks records migrated/managed digitally.

- Attendance and result generation time reduced compared to the manual baseline.

- Role-based access enforced with zero unauthorized cross-role access incidents.

- Positive usability feedback from students and faculty during Sprint Reviews/UAT.

## Project Constraints

- Fixed academic-term timeline aligned to the institution's semester calendar.

- Must integrate with existing institutional data (student and course master data).

- Limited development team size, requiring careful Sprint scoping.

- Data privacy and security requirements for student academic records.

## Expected Software Capabilities

- Student, Course, Attendance, and Marks/Academic Performance management.

- Secure authentication with role-based access control.

- Automated notifications for attendance, examinations, and results.

- Institution-wide reporting across all modules.

# 3. Scrum Team Structure & Roles and Responsibilities

The mini-project team is organized as a single Scrum Team of five members holding the three standard Scrum roles below. Role assignment is illustrative and can be mapped to actual team members at project kickoff.

## Product Owner

- Defining product requirements in collaboration with stakeholders.

- Prioritizing and continuously refining the Product Backlog.

- Representing stakeholder interests (students, faculty, administration) throughout the project.

- Accepting completed work at the end of each Sprint against Acceptance Criteria.

## Scrum Master

- Facilitating Sprint Planning, Daily Scrum, Sprint Review, and Sprint Retrospective.

- Removing impediments raised by the Development Team.

- Ensuring Agile/Scrum practices are followed consistently.

- Supporting collaboration between the Product Owner and the Development Team.

## Development Team

- Designing the application architecture and database schema.

- Writing and reviewing code for each Sprint's committed User Stories.

- Testing software (unit, integration, and user-acceptance support).

- Preparing technical and user documentation.

- Demonstrating completed features at Sprint Review.

## Team Structure Summary

| Role | Count | Primary Focus |
| --- | --- | --- |
| Product Owner | 1 | Backlog ownership, prioritization, stakeholder representation |
| Scrum Master | 1 | Process facilitation, impediment removal |
| Development Team | 3 | Design, development, testing, documentation |

# 4. Epic Documentation

## Epic 1: Student Management

Covers the complete lifecycle of a student record — from onboarding to eventual deactivation — forming the core data foundation the rest of the platform depends on.

Features: Student Registration, Student Profile Management, Student Search, Student Update, Student Deletion

## Epic 2: Course Management

Enables administrators to define the courses offered by the institution and manage student enrollment against them.

Features: Add Course, Update Course, Assign Students, View Course Details

## Epic 3: Attendance Management

Provides faculty with tools to record day-to-day attendance and gives students visibility into their own attendance standing.

Features: Record Attendance, View Attendance, Attendance Reports

## Epic 4: Marks and Academic Performance

Manages entry, correction, and calculation of academic results, producing consolidated result sheets for students.

Features: Enter Marks, Update Marks, Calculate Grades, Generate Result Sheets

## Epic 5: Authentication and Security

Secures the platform with role-appropriate access, ensuring each user type sees only the functionality relevant to them.

Features: User Login, Logout, Password Reset, Role-Based Access Control

## Epic 6: Notifications

Keeps students and guardians informed of time-sensitive academic events through timely, automated alerts.

Features: Attendance Alerts, Examination Notifications, Result Notifications

## Epic 7: Reporting

Provides institution-wide, cross-cutting reports that consolidate data from the Student, Attendance, and Academic Performance modules for decision-making.

Features: Student Reports, Attendance Reports (Institution-wide), Performance Reports, Course Reports

# 5. User Story Repository & Acceptance Criteria

Every feature identified across the seven Epics is expressed below as a User Story in the standard Agile format, together with the Acceptance Criteria that define its definition of “Done.”

## Epic 1: Student Management

### Student Registration

As an Admin/Registrar, I want to register new students into the system so that their academic records can be created and tracked from day one.

Acceptance Criteria:

- Registration form captures name, contact details, and enrollment ID.

- Duplicate enrollment IDs are rejected with a clear error.

- A unique Student ID is generated on successful registration.

- Registered student appears immediately in the student list.

- Confirmation message is shown after successful registration.

### Student Profile Management

As a Student, I want to view and update my profile information so that my personal details stay accurate and current.

Acceptance Criteria:

- Student can view all editable profile fields.

- Changes are validated before saving.

- Updated profile is reflected immediately across the platform.

- Sensitive fields (Student ID, enrollment year) remain read-only.

### Student Search

As an Admin, I want to search for students by name, ID, or course so that I can quickly locate the record I need.

Acceptance Criteria:

- Search returns results as the admin types (or on submit).

- Search supports partial name and exact ID matches.

- No-match searches show a helpful empty state.

- Results link directly to the full student profile.

### Student Update

As an Admin, I want to update existing student records so that information stays current after changes such as address or course changes.

Acceptance Criteria:

- Admin can edit any non-system-generated field.

- Update history is logged with timestamp and editor.

- Validation prevents invalid data (e.g., blank required fields).

- Success confirmation is displayed after saving.

### Student Deletion

As an Admin, I want to deactivate or remove a student record so that outdated or erroneous records don't clutter the system.

Acceptance Criteria:

- Admin is shown a confirmation prompt before deletion.

- Deletion is soft (deactivation) by default to preserve historical data.

- Deactivated students no longer appear in active search/reports.

- Action is logged for audit purposes.

## Epic 2: Course Management

### Add Course

As an Admin, I want to add a new course to the system so that it becomes available for student enrollment.

Acceptance Criteria:

- Course form requires course name, code, and credit value.

- Duplicate course codes are rejected.

- New course appears in the course catalog immediately.

- Confirmation is shown on successful creation.

### Update Course

As an Admin, I want to update course details so that course information (schedule, faculty, credits) stays accurate.

Acceptance Criteria:

- Admin can edit all course fields except the course code.

- Changes are reflected for all enrolled students.

- Validation prevents blank required fields.

- Update is logged with timestamp.

### Assign Students

As an Admin, I want to assign students to a course so that enrollment records are accurately maintained.

Acceptance Criteria:

- Admin can search and select students to assign.

- System prevents duplicate enrollment in the same course.

- Assigned students appear in the course roster instantly.

- Assignment can be reversed (un-enroll) if needed.

### View Course Details

As a Student/Faculty, I want to view course details so that I know the syllabus, schedule, and assigned faculty.

Acceptance Criteria:

- Course detail page shows name, code, credits, schedule, and faculty.

- Enrolled student list is visible to faculty.

- Page loads within acceptable time for a typical course size.

- Details are read-only for students.

## Epic 3: Attendance Management

### Record Attendance

As a Faculty Member, I want to record student attendance so that attendance records remain accurate and updated.

Acceptance Criteria:

- Faculty can select a course.

- Faculty can select a lecture date.

- Faculty can mark attendance for each enrolled student.

- Attendance records are saved successfully.

- Attendance reports can be generated from saved records.

### View Attendance

As a Student, I want to view my attendance record so that I can track my eligibility for examinations.

Acceptance Criteria:

- Student can view attendance percentage per course.

- Attendance is broken down by lecture date.

- A low-attendance warning is shown below the eligibility threshold.

- Data reflects the latest recorded session.

### Attendance Reports

As a Faculty Member, I want to generate attendance reports for my course so that I can review attendance trends and flag at-risk students.

Acceptance Criteria:

- Report can be filtered by date range and course.

- Report shows per-student attendance percentage.

- Students below the minimum threshold are highlighted.

- Report can be exported (PDF/Excel).

## Epic 4: Marks and Academic Performance

### Enter Marks

As a Faculty Member, I want to enter student marks for an assessment so that academic performance is accurately recorded.

Acceptance Criteria:

- Faculty can select course, assessment type, and student.

- Marks are validated against the maximum allowed marks.

- Entered marks are saved against the correct assessment.

- Confirmation is shown on successful save.

### Update Marks

As a Faculty Member, I want to update previously entered marks so that data-entry errors can be corrected.

Acceptance Criteria:

- Faculty can locate and edit a previously saved mark.

- Change is validated the same way as new entries.

- Edit history (old value, new value, editor) is logged.

- Updated marks reflect immediately in grade calculations.

### Calculate Grades

As a System, I want to automatically calculate grades from entered marks so that grading is consistent, accurate, and free of manual error.

Acceptance Criteria:

- Grade boundaries follow the institution's grading policy.

- Grades recalculate automatically when marks are updated.

- Calculated grade is displayed alongside the raw marks.

- Edge cases (missing marks) are handled without crashing the calculation.

### Generate Result Sheets

As an Admin, I want to generate consolidated result sheets so that students receive a complete academic performance summary.

Acceptance Criteria:

- Result sheet aggregates marks and grades across all assessments.

- Sheet can be generated per student or per course/class.

- Generated sheet can be downloaded as PDF.

- Only finalized (locked) marks are included in the result sheet.

## Epic 5: Authentication and Security

### User Login

As a Registered User, I want to log in to the platform so that I can access my dashboard and role-specific features.

Acceptance Criteria:

- Login page loads successfully.

- Registered users can log in.

- Invalid credentials display appropriate error messages.

- Successful login redirects to the dashboard.

- Session management functions correctly.

### Logout

As a User, I want to log out of the platform so that my session ends securely on a shared or public device.

Acceptance Criteria:

- Logout is accessible from every authenticated page.

- Session/token is invalidated immediately on logout.

- User is redirected to the login page.

- Back-navigation after logout does not restore the session.

### Password Reset

As a User, I want to reset my password so that I can regain access if I forget my credentials.

Acceptance Criteria:

- User can request a reset via registered email.

- Reset link/token expires after a limited time.

- New password must meet complexity requirements.

- User is notified once the password has been changed.

### Role-Based Access Control

As a System Administrator, I want to configure role-based access so that users only see and use features relevant to their role (Student, Faculty, Admin).

Acceptance Criteria:

- Each role has a clearly defined permission set.

- Unauthorized actions are blocked at both UI and API level.

- Role assignment can be changed by an administrator.

- Access attempts outside a role's permissions are logged.

## Epic 6: Notifications

### Attendance Alerts

As a Student, I want to receive attendance alerts so that I am notified promptly when my attendance drops near the minimum threshold.

Acceptance Criteria:

- Alert triggers automatically when attendance crosses the threshold.

- Alert is delivered via the platform and/or email.

- Alert includes the current attendance percentage.

- Duplicate alerts are not sent for the same threshold breach.

### Examination Notifications

As a Student, I want to receive examination notifications so that I don't miss exam schedules or venue changes.

Acceptance Criteria:

- Notification is sent when an exam is scheduled or updated.

- Notification includes date, time, and venue.

- Students only receive notifications for courses they are enrolled in.

- Notification is logged as read/unread.

### Result Notifications

As a Student, I want to receive result notifications so that I know as soon as my results are published.

Acceptance Criteria:

- Notification is triggered when a result sheet is finalized.

- Notification links directly to the result sheet.

- Notification is sent only once per result publication.

- Students can view a history of past result notifications.

## Epic 7: Reporting

### Student Reports

As an Admin, I want to generate consolidated student reports so that institutional records are readily available for audits and accreditation.

Acceptance Criteria:

- Report can be filtered by course, batch, or enrollment year.

- Report includes core demographic and enrollment data.

- Report can be exported to PDF/Excel.

- Report generation completes within an acceptable time for typical batch sizes.

### Attendance Reports (Institution-wide)

As an Admin, I want to generate institution-wide attendance reports so that I can monitor attendance trends across all courses, not just one.

Acceptance Criteria:

- Report aggregates attendance across all active courses.

- Report can be filtered by department or date range.

- Courses/students below the attendance threshold are flagged.

- Report can be exported for record-keeping.

### Performance Reports

As an Admin/Faculty, I want to generate academic performance reports so that performance trends can be analyzed across courses and batches.

Acceptance Criteria:

- Report shows grade distribution per course/batch.

- Report can be filtered by academic term.

- Report highlights courses with unusually low pass rates.

- Report supports export for further analysis.

### Course Reports

As an Admin, I want to generate course reports so that enrollment and completion data is available for planning.

Acceptance Criteria:

- Report shows enrollment count and completion status per course.

- Report can be filtered by term/semester.

- Report can be exported to PDF/Excel.

- Inactive/archived courses are excluded by default.

# 6. Prioritized Product Backlog

The Product Backlog consolidates every User Story and prioritizes it by business value, user importance, technical dependency, and implementation complexity.

| Priority | Epic | User Story | Points |
| --- | --- | --- | --- |
| High | Student Management | Student Registration | 5 |
| High | Student Management | Student Search | 2 |
| High | Course Management | Add Course | 3 |
| High | Course Management | Assign Students | 5 |
| High | Attendance Management | Record Attendance | 5 |
| High | Marks and Academic Performance | Enter Marks | 5 |
| High | Marks and Academic Performance | Calculate Grades | 5 |
| High | Authentication and Security | User Login | 3 |
| High | Authentication and Security | Logout | 1 |
| High | Authentication and Security | Role-Based Access Control | 8 |
| Medium | Student Management | Student Profile Management | 3 |
| Medium | Student Management | Student Update | 3 |
| Medium | Course Management | Update Course | 2 |
| Medium | Course Management | View Course Details | 2 |
| Medium | Attendance Management | View Attendance | 2 |
| Medium | Attendance Management | Attendance Reports | 5 |
| Medium | Marks and Academic Performance | Update Marks | 3 |
| Medium | Marks and Academic Performance | Generate Result Sheets | 8 |
| Medium | Authentication and Security | Password Reset | 3 |
| Medium | Notifications | Attendance Alerts | 3 |
| Medium | Notifications | Examination Notifications | 3 |
| Medium | Reporting | Student Reports | 5 |
| Medium | Reporting | Performance Reports | 5 |
| Low | Student Management | Student Deletion | 2 |
| Low | Notifications | Result Notifications | 3 |
| Low | Reporting | Attendance Reports (Institution-wide) | 3 |
| Low | Reporting | Course Reports | 3 |

# 7. Story Point Estimation Sheet

Effort was estimated collaboratively using Planning Poker, with the following Fibonacci-based scale:

| Story Points | Complexity |
| --- | --- |
| 1 | Very Easy |
| 2 | Easy |
| 3 | Moderate |
| 5 | Difficult |
| 8 | Very Difficult |
| 13 | Highly Complex |

## Estimation by User Story

| Epic | User Story | Story Points |
| --- | --- | --- |
| Student Management | Student Registration | 5 |
| Student Management | Student Profile Management | 3 |
| Student Management | Student Search | 2 |
| Student Management | Student Update | 3 |
| Student Management | Student Deletion | 2 |
| Course Management | Add Course | 3 |
| Course Management | Update Course | 2 |
| Course Management | Assign Students | 5 |
| Course Management | View Course Details | 2 |
| Attendance Management | Record Attendance | 5 |
| Attendance Management | View Attendance | 2 |
| Attendance Management | Attendance Reports | 5 |
| Marks and Academic Performance | Enter Marks | 5 |
| Marks and Academic Performance | Update Marks | 3 |
| Marks and Academic Performance | Calculate Grades | 5 |
| Marks and Academic Performance | Generate Result Sheets | 8 |
| Authentication and Security | User Login | 3 |
| Authentication and Security | Logout | 1 |
| Authentication and Security | Password Reset | 3 |
| Authentication and Security | Role-Based Access Control | 8 |
| Notifications | Attendance Alerts | 3 |
| Notifications | Examination Notifications | 3 |
| Notifications | Result Notifications | 3 |
| Reporting | Student Reports | 5 |
| Reporting | Attendance Reports (Institution-wide) | 3 |
| Reporting | Performance Reports | 5 |
| Reporting | Course Reports | 3 |

Total Estimated Effort: 100 Story Points

# 8. Sprint Planning & Sprint Backlog

The Product Backlog is organized into five two-week Sprints, sequenced so that foundational and security-critical capabilities are delivered first.

## Sprint 1 — 15 Story Points

Sprint Goal: Establish project foundation and deliver secure authentication.

Sprint Backlog (User Stories):

- User Login (Authentication and Security) — 3 pts

- Logout (Authentication and Security) — 1 pts

- Password Reset (Authentication and Security) — 3 pts

- Role-Based Access Control (Authentication and Security) — 8 pts

Supporting Activities:

- Repository initialization and branching strategy.

- CI pipeline and coding-standard setup.

- Base UI shell and navigation layout.

## Sprint 2 — 15 Story Points

Sprint Goal: Deliver the full Student Management module.

Sprint Backlog (User Stories):

- Student Registration (Student Management) — 5 pts

- Student Profile Management (Student Management) — 3 pts

- Student Search (Student Management) — 2 pts

- Student Update (Student Management) — 3 pts

- Student Deletion (Student Management) — 2 pts

Supporting Activities:

- Unit and integration testing for student CRUD flows.

## Sprint 3 — 24 Story Points

Sprint Goal: Deliver Course Management and Attendance Management.

Sprint Backlog (User Stories):

- Add Course (Course Management) — 3 pts

- Update Course (Course Management) — 2 pts

- Assign Students (Course Management) — 5 pts

- View Course Details (Course Management) — 2 pts

- Record Attendance (Attendance Management) — 5 pts

- View Attendance (Attendance Management) — 2 pts

- Attendance Reports (Attendance Management) — 5 pts

Supporting Activities:

- Regression testing across Student + Course + Attendance modules.

## Sprint 4 — 21 Story Points

Sprint Goal: Deliver Marks Entry and Academic Performance calculation.

Sprint Backlog (User Stories):

- Enter Marks (Marks and Academic Performance) — 5 pts

- Update Marks (Marks and Academic Performance) — 3 pts

- Calculate Grades (Marks and Academic Performance) — 5 pts

- Generate Result Sheets (Marks and Academic Performance) — 8 pts

Supporting Activities:

- Validation of grade-calculation logic against institution policy.

## Sprint 5 — 25 Story Points

Sprint Goal: Deliver Notifications and institution-wide Reporting; project hardening.

Sprint Backlog (User Stories):

- Attendance Alerts (Notifications) — 3 pts

- Examination Notifications (Notifications) — 3 pts

- Result Notifications (Notifications) — 3 pts

- Student Reports (Reporting) — 5 pts

- Attendance Reports (Institution-wide) (Reporting) — 3 pts

- Performance Reports (Reporting) — 5 pts

- Course Reports (Reporting) — 3 pts

Supporting Activities:

- End-to-end testing, UAT support, and release preparation.

# 9. Scrum Board

Snapshot of the Scrum Board midway through Sprint 3, illustrating how work items move across the workflow columns.

| Backlog | To Do | In Progress | Testing | Completed |
| --- | --- | --- | --- | --- |
| Enter Marks | Update Course | Assign Students | Attendance Reports | User Login |
| Calculate Grades | View Course Details | Record Attendance |  | Logout |
| Generate Result Sheets |  |  |  | Password Reset |
| Attendance Alerts |  |  |  | Role-Based Access Control |
| Student Reports |  |  |  | Add Course |
|  |  |  |  | Student Registration |
|  |  |  |  | Student Profile Management |
|  |  |  |  | Student Search |
|  |  |  |  | Student Update |
|  |  |  |  | Student Deletion |

The board is updated continuously through the Sprint as the Development Team pulls items from To Do through to Completed.

# 10. Burndown Chart

The Release Burndown Chart tracks total remaining Story Points against the ideal, evenly-distributed pace across the five Sprints.

Total scope: 100 Story Points across 5 Sprints. Actual delivery tracked close to the ideal line, with Sprint 3 and Sprint 5 carrying the heaviest load (multi-Epic Sprints).

# 11. Simulated Scrum Ceremonies

## Sprint Planning

At the start of each Sprint, the team selects User Stories from the top of the Product Backlog, re-confirms Story Point estimates, and agrees on a single Sprint Goal (see Section 8 for each Sprint's goal and committed stories).

## Daily Scrum — Sample Log (Sprint 2, Days 1-3)

| Day | Completed Yesterday | Plan for Today | Impediments |
| --- | --- | --- | --- |
| Day 1 | Sprint kickoff; reviewed Student Management stories | Design student data model and registration API | None |
| Day 2 | Student data model and registration API implemented | Build registration UI form and validation | Waiting on UI component library setup |
| Day 3 | Registration UI complete; started Student Search | Implement search API and results UI | None |

## Sprint Review — Summary (per Sprint)

| Sprint | Features Demonstrated | Stakeholder Feedback |
| --- | --- | --- |
| Sprint 1 | Login, Logout, Password Reset, RBAC | Positive; requested clearer error messages on failed login. |
| Sprint 2 | Student Registration, Profile, Search, Update, Deletion | Approved; requested bulk-search by course as a future enhancement. |
| Sprint 3 | Add/Update Course, Assign Students, Attendance recording & reports | Approved; faculty requested a quicker attendance-marking flow. |
| Sprint 4 | Marks entry/update, automated grade calculation, result sheets | Approved; admin requested downloadable result sheets in bulk. |
| Sprint 5 | Notifications and institution-wide reporting | Approved; positive feedback on automated alerts. |

## Sprint Retrospective — Summary (per Sprint)

| What Went Well | Challenges Faced | Improvements for Next Sprint |
| --- | --- | --- |
| Clear Sprint Goals kept the team focused | Underestimated RBAC complexity in Sprint 1 | Add a technical spike before estimating security-heavy stories |
| Good collaboration between Dev Team and Product Owner | Minor delays from UI library setup | Finalize shared UI components before Sprint start |
| Faster delivery once patterns from Sprint 1-2 were reused | Multi-Epic Sprints (3 and 5) felt crowded | Balance Sprint scope more evenly across Epics |

# 12. Agile Framework Comparison

A comparative study of the Agile frameworks introduced in the syllabus, evaluated against criteria relevant to this project.

| Framework | Typical Team Size | Cadence | Process Overhead | Best Suited For | Fit for This Project |
| --- | --- | --- | --- | --- | --- |
| Scrum | Small (5-9) | Fixed-length Sprints | Moderate | Products needing frequent, predictable increments | High |
| Kanban | Any size | Continuous flow | Low | Support/maintenance or steady-flow work | Medium |
| Extreme Programming (XP) | Small (2-10) | Very short iterations | Low, engineering-heavy | High technical-quality, rapidly changing code | Medium |
| Lean Development | Any size | Continuous, waste-driven | Low | Efficiency-focused, resource-constrained teams | Medium |
| Large Scale Scrum (LeSS) | Multiple Scrum teams | Synchronized Sprints | Moderate-High | Large products needing several coordinated Scrum teams | Low |
| Scaled Agile Framework (SAFe) | Enterprise-wide | Program Increments | High | Large enterprises with many dependent teams | Low |
| Scrum@Scale | Multiple Scrum teams | Scaled Sprints via Scrum of Scrums | Moderate-High | Organizations scaling Scrum without a heavyweight framework | Low |

## Recommendation

Scrum is recommended for the Student Record and Academic Management Platform. The project has a single, moderately sized development team, a fixed academic-term timeline, and a Product Owner (representing institutional stakeholders) who benefits from reviewing tangible increments every Sprint. Scrum's fixed-length Sprints, defined roles, and built-in ceremonies (Planning, Daily Scrum, Review, Retrospective) map directly onto these needs without the coordination overhead of scaled frameworks such as SAFe or LeSS, which are designed for multiple, dependent teams working on much larger products.

# 13. Project Timeline & Release Roadmap

| Sprint | Duration | Milestone / Release |
| --- | --- | --- |
| Sprint 1 | Weeks 1-2 | Secure platform foundation — authentication & RBAC live |
| Sprint 2 | Weeks 3-4 | Student Management module released |
| Sprint 3 | Weeks 5-6 | Course Management and Attendance Management released |
| Sprint 4 | Weeks 7-8 | Marks entry and automated academic performance calculation released |
| Sprint 5 | Weeks 9-10 | Notifications and institution-wide Reporting released; final UAT and hardening |

End of Sprint 5 marks the project's MVP release, covering all seven Epics identified in the Product Backlog and ready for institutional rollout.

# 14. Conclusion

This Agile Project Planning Report operationalizes the Unit-1 Product Vision for the Student Record and Academic Management Platform into a complete, executable Agile plan: defined Scrum roles, seven Epics broken into 27 User Stories with Acceptance Criteria, a prioritized 100-point Product Backlog, a five-Sprint delivery plan, a live Scrum Board, a Release Burndown Chart, simulated Scrum ceremonies, and a justified choice of Scrum as the governing framework. Together these artifacts form the Complete Agile Documentation deliverable for Unit 2.